## Agile Project Plan-Example
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Product Release | Alex B. | 2022-09-02 | 2022-10-10 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2022-09-03 | 2022-09-13 | 10 | Complete
| Feature 1 |  | Frank C. |  | 2022-09-03 | 2022-09-07 | 4 | Complete
| Feature 2 |  | Jacob S. |  | 2022-09-07 | 2022-09-12 | 5 | Complete
| Feature 3 |  | Jacob S. |  | 2022-09-09 | 2022-09-13 | 4 | Overdue
| Sprint 2 |  | Jacob S. |  | 2022-09-16 | 2022-09-24 | 8 | In Progress
| Feature 4 |  | Alex B. |  | 2022-09-16 | 2022-09-17 | 1 | In Progress
| Feature 5 |  | Frank C. |  | 2022-09-17 | 2022-09-21 | 4 | Not Started
| Feature 6 |  | Shari W. |  | 2022-09-22 | 2022-09-24 | 2 | Not Started
| Sprint 3 |  | Shari W. |  | 2022-09-25 | 2022-10-05 | 10 | Not Started
| Feature 7 |  | Alex B. |  | 2022-09-25 | 2022-09-29 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2022-09-24 | 2022-10-02 | 8 | Not Started
| Feature 9 |  | Jacob S. |  | 2022-10-02 | 2022-10-05 | 3 | Not Started

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Fake News Detection |  | 2020-10-27 | 2021-04-26 |  |  |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Data Acquisition and EDA |  |  |  | 2020-10-27 | 2020-11-10 | 15 | Completed
| Data Collection |  |  |  | 2020-10-27 | 2020-11-10 | 15 | Completed
| Data Acquisition and EDA |  |  |  | 2020-11-11 | 2020-11-25 | 15 | In Progress
| Data Cleaning and ETL |  |  |  | 2020-11-11 | 2020-11-19 | 9 | Completed
| Exploratory Data Analysis |  |  |  | 2020-11-20 | 2020-11-25 | 6 | In Progress
| Research Feasibility of NLP |  |  |  | 2020-11-26 | 2020-11-29 | 4
| Investigate NLP Libraries |  |  |  | 2020-11-26 | 2020-11-27 | 2
| Investigate NLP Algorithms |  |  |  | 2020-11-28 | 2020-11-29 | 2
| Research ML Algorithms |  |  |  | 2020-11-30 | 2020-12-03 | 4
Support Vector Machine
Random Forest Classifier
Naïve Bayes Classifier
| Research Feasibility of NLP |  |  |  | 2020-12-04 | 2020-12-07 | 4
Investigate NLP Libraries
Investigate NLP Algorithms
| Research Feasibility of Neural Networks |  |  |  | 2020-12-13 | 2020-12-16 | 4
Investigate Neural Networks Libraries
Investigate integration with model
| Investigate existing sysytems |  |  |  | 2020-12-17 | 2020-12-20 | 4
Research existing systems based on NLP
Research existing systems based on Neural Networks
Identify major techniques used
| Begin Model Building Process |  |  |  | 2020-12-21 | 2020-12-28 | 8
Identify libraries and algorithms to be used
Create cloud and local repository
Start implementing code
| Continue Model Building |  |  |  | 2020-12-29 | 2021-01-12 | 15 |  | Start Testing Process
| Continue Model Building |  |  |  | 2021-01-13 | 2021-01-27 | 15
| Continue Model Building |  |  |  | 2021-01-28 | 2021-02-11 | 15
| Final Unit Testing of Models Created |  |  |  | 2021-02-12 | 2021-02-15 | 4
Unit tests for each model
| Research UI integration |  |  |  | 2021-02-16 | 2021-02-23 | 8
Investigate different UI platforms
Compare the platforms
Identify suitable platform for integration
| Start Developing UI |  |  |  | 2021-02-24 | 2021-03-03 | 8
Understand the software
Design the User Interface
| Integrate with Model |  |  |  | 2021-03-04 | 2021-03-18 | 15
Understand integration process
Begin integrating models with UI
| Final Integration Testing |  |  |  | 2021-03-19 | 2021-03-22 | 4
Develop Test Cases
Execute Test Cases
| Research AWS/ Heroku/ Azure |  |  |  | 2021-03-23 | 2021-03-30 | 8
Investigate different deployment platforms
Identify a suitable option
Begin Deployment Process
| Deployment on AWS/ Heroku/ Azure |  |  |  | 2021-03-31 | 2021-04-09 | 10
Continue Deployment Process
Finalize Deployment

## Dates from Guidelines Document
Important Dates (Tentative)
Tasks | Date
Project Proposal (Store in Moodle) | 2020-10-27
Interim Presentation, Report and Prototypes - Research Of Technologies/Application Domain - Prototypes - Requirements for final system - Presentation | 2021-01-18
Final Version and Report - Demo of results - Software - Final Report/Thesis | 2021-04-26